## Consulting Gantt Chart
Digital Marketing Consulting Gantt Chart
Company Name: |  | Binary Quest Limited
Consultant |  | Zakaria Mohammad
50
Task | RP | Start Date | Days | End Date | time axis 2023-07-16 to 2023-08-30
IDM STRATEGY | ZAK | 2023-07-16 | 1 | 2023-07-30
-- Requirement Collections | ZAK | 2023-07-16 | 1 | 2023-07-27 | bar: 2023-07-16 to 2023-07-20; 2023-07-23 to 2023-07-27
-- Requirement Understanding | ZAK | 2023-07-16 | 15 | 2023-07-31 | bar: 2023-07-16 to 2023-07-20; 2023-07-23 to 2023-07-27; 2023-07-30 to 2023-07-31
-- Website Strategy | ZAK | 2023-07-31 | 6 | 2023-08-06 | bar: 2023-07-31 to 2023-08-03; 2023-08-06
-- Social Media Strategy | ZAK | 2023-08-07 | 6 | 2023-08-13 | bar: 2023-08-07 to 2023-08-10; 2023-08-13 to 2023-08-17; 2023-08-20
-- SEO TO-DO-LIST | ZAK | 2023-08-14 | 6 | 2023-08-20
CONTENT STRATEGY | ZAK | 2023-08-07 | 21 | 2023-08-28
-- Set goals and objectives | ZAK | 2023-08-07 | 2 | 2023-08-09 | bar: 2023-08-07 to 2023-08-09
-- Content planners | ZAK | 2023-08-08 | 20 | 2023-08-28 | bar: 2023-08-08 to 2023-08-10
-- Distribution channels | ZAK | 2023-08-13 | 8 | 2023-08-21 | bar: 2023-08-13 to 2023-08-14
CX WEBSITE - HTML | ZAK | 2023-08-17 | 34 | 2023-09-20
-- Home page HTML | ZAK | 2023-08-24 | 3 | 2023-08-27
-- Company Listing | ZAK | 2023-08-27 | 2 | 2023-08-29
-- Company Detail | ZAK | 2023-08-30 | 1 | 2023-08-31
-- Category Listing | ZAK | 2023-09-03 | 1 | 2023-09-04
-- Category Detail | ZAK | 2023-09-05 | 1 | 2023-09-06
-- City Page Listing | ZAK | 2023-09-06 | 1 | 2023-09-07
-- City Page Detail | ZAK | 2023-09-09 | 2 | 2023-09-11
-- Blog Listing | ZAK | 2023-09-12 | 1 | 2023-09-13
-- Blog Detail | ZAK | 2023-09-14 | 3 | 2023-09-17
-- Static Page | ZAK | 2023-09-18 | 2 | 2023-09-20
CONTENT ARCHITECTURE | ZAK | 2023-08-24 | 13 | 2023-09-06
-- 300 Keyword List | ZAK | 2023-08-27 | 4 | 2023-08-31
-- Content Architecture - 4X | ZAK | 2023-09-03 | 8 | 2023-09-11
-- Social Media Template - 4X | ZAK | 2023-09-12 | 6 | 2023-09-18
SOCIAL MEDIA OPTIMIZATION | ZAK | 2023-08-21 | 20 | 2023-09-10
-- GBP Profile | ZAK | 2023-08-22 | 6 | 2023-08-28 | bar: 2023-08-07 to 2023-08-08
-- GBP Post - 4X | ZAK | 2023-08-22 | 6 | 2023-08-28 | bar: 2023-08-08 to 2023-08-10
-- Facebook Profile | ZAK | 2023-08-29 | 6 | 2023-09-04 | bar: 2023-08-13 to 2023-08-14
-- Facebook Post - 4X | ZAK | 2023-08-29 | 6 | 2023-09-04 | bar: 2023-08-16 to 2023-08-17; 2023-08-20
-- Youtube Profile | ZAK | 2023-09-05 | 2 | 2023-09-07 | bar: 2023-08-06 to 2023-08-07
-- Youtube Video - 2X | ZAK | 2023-08-29 | 9 | 2023-09-07 | bar: 2023-08-13 to 2023-08-17; 2023-08-20 to 2023-08-24
-- Social Media Calendar | ZAK | 2023-09-10 | 0 | 2023-09-10 | bar: 2023-08-27 to 2023-08-29
-- Directory Listing – 4X | ZAK | 2023-08-25 | 16 | 2023-09-10 | bar: 2023-08-17; 2023-08-20 to 2023-08-24
FEEDBACK & QC | ZAK | 2023-08-24 | 35 | 2023-09-28
-- Platform Rediness | ZAK | 2023-08-01 | 54 | 2023-09-24 | bar: 2023-08-01 to 2023-08-03; 2023-08-06 to 2023-08-10; 2023-08-13 to 2023-08-17; 2023-08-20 to 2023-08-24; 2023-08-27 to 2023-08-30
-- Webmaster Submission | ZAK | 2023-09-21 | 7 | 2023-09-28
-- Monthly Content Calender | ZAK | 2023-09-25 | 3 | 2023-09-28

## Monthly KPI Target
Monthly Content & SEO Marketing ¦ KPI Target
Company Name: |  | Binary Quest Limited |  |  |  | Q4 | 2023 |  | Q1 | 2024 |  | Q2 | 2024 |  | Q3 | 2024 |  | Q4 | 2024
Consultant |  | Zakaria Mohammad
Indicators | RP | Start Date | Days | End Date | 2023-09-30 | 2023-10-31 | 2023-11-30 | 2023-12-31 | 2024-01-31 | 2024-02-29 | 2024-03-31 | 2024-04-30 | 2024-05-31 | 2024-06-30 | 2024-07-31 | 2024-08-31 | 2024-09-30 | 2024-10-31 | 2024-11-29
Business profile verification | ZAK | 2023-09-03 | 363 | 2024-08-31 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
Q - Closing | ZAK | 2023-09-03 | 363 | 2024-08-31 | 15 | 30 | 45 | 60 | 75 | 90 | 105 | 120 | 135 | 150 | 165 | 180 | 195 | 210 | 225
Landing pages | ZAK | 2023-09-03 | 363 | 2024-08-31 | 3 | 3 | 4 | 3 | 4 | 3 | 3 | 3 | 4 | 3 | 4 | 3 | 3 | 3 | 4
Q - Closing | ZAK | 2023-09-03 | 363 | 2024-08-31 | 3 | 6 | 10 | 13 | 17 | 20 | 23 | 26 | 30 | 33 | 37 | 40 | 43 | 46 | 50
Blog pages | ZAK | 2023-09-03 | 363 | 2024-08-31 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Q - Closing | ZAK | 2023-09-03 | 363 | 2024-08-31 | 2 | 4 | 6 | 8 | 10 | 12 | 14 | 16 | 18 | 20 | 22 | 24 | 26 | 28 | 30
City pages | ZAK | 2023-09-03 | 363 | 2024-08-31 | 3 | 3 | 9 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Q - Closing | ZAK | 2023-09-03 | 363 | 2024-08-31 | 3 | 6 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 26
Google page indexed | ZAK | 2023-09-03 | 363 | 2024-08-31 | 30 | 30 | 30 | 20 | 20 | 20 | 40 | 30 | 30 | 50 | 50 | 50 | 70 | 70 | 60
Q - Closing | ZAK | 2023-09-03 | 363 | 2024-08-31 | 30 | 60 | 90 | 110 | 130 | 150 | 190 | 220 | 250 | 300 | 350 | 400 | 470 | 540 | 600
Organic keywords | ZAK | 2023-09-03 | 363 | 2024-08-31 | 20 | 40 | 60 | 50 | 60 | 70 | 120 | 180 | 200 | 120 | 160 | 180 | 180 | 200 | 220
Q - Closing | ZAK | 2023-09-03 | 363 | 2024-08-31 | 20 | 60 | 120 | 170 | 230 | 300 | 420 | 600 | 800 | 920 | 1080 | 1260 | 1440 | 1640 | 1860
Organic Traffic Impression | ZAK | 2023-09-03 | 363 | 2024-08-31 | 800 | 1000 | 1200 | 1000 | 1200 | 1500 | 1200 | 1500 | 1800 | 1400 | 1500 | 1600 | 1500 | 1800 | 2000
Q - Closing | ZAK | 2023-09-03 | 363 | 2024-08-31 | 800 | 1800 | 3000 | 4000 | 5200 | 6700 | 7900 | 9400 | 11200 | 12600 | 14100 | 15700 | 17200 | 19000 | 21000
Paid Traffic | ZAK | 2023-09-03 | 363 | 2024-08-31
Q - Closing | ZAK | 2023-09-03 | 363 | 2024-08-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pages with first impressions | ZAK | 2023-09-03 | 363 | 2024-08-31 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 2 | 2 | 2
Q - Closing | ZAK | 2023-09-03 | 363 | 2024-08-31 | 0 | 0 | 1 | 1 | 2 | 3 | 4 | 5 | 6 | 8 | 10 | 11 | 13 | 15 | 17
GA: Acquisition Overview | ZAK | 2023-09-03 | 363 | 2024-08-31 | 500 | 700 | 800 | 600 | 700 | 800 | 900 | 1200 | 1500 | 1200 | 1600 | 2000 | 2400 | 3000 | 3600
Q - Closing | ZAK | 2023-09-03 | 363 | 2024-08-31 | 500 | 1200 | 2000 | 2600 | 3300 | 4100 | 5000 | 6200 | 7700 | 8900 | 10500 | 12500 | 14900 | 17900 | 21500
AHREF: Domain Rating (DR) | ZAK | 2023-09-03 | 363 | 2024-08-31 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1
Q - Closing | ZAK | 2023-09-03 | 363 | 2024-08-31 | 0 | 0 | 1 | 1 | 2 | 2 | 3 | 3 | 4 | 4 | 5 | 5 | 6 | 6 | 7
AHREF: URL Rating (UR) | ZAK | 2023-09-03 | 363 | 2024-08-31 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1
Q - Closing | ZAK | 2023-09-03 | 363 | 2024-08-31 | 0 | 1 | 2 | 2 | 3 | 4 | 4 | 5 | 6 | 6 | 7 | 7 | 8 | 8 | 9
AHREF: Backlinks | ZAK | 2023-09-03 | 363 | 2024-08-31 | 12 | 18 | 20 | 10 | 10 | 10 | 14 | 16 | 20 | 20 | 30 | 20 | 40 | 50 | 60
Q - Closing | ZAK | 2023-09-03 | 363 | 2024-08-31 | 12 | 30 | 50 | 60 | 70 | 80 | 94 | 110 | 130 | 150 | 180 | 200 | 240 | 290 | 350
AHREF: Traffic value | ZAK | 2023-09-03 | 363 | 2024-08-31 | 0 | 0 | 10 | 0 | 10 | 10 | 20 | 30 | 40 | 20 | 30 | 30 | 50 | 70 | 80
Q - Closing | ZAK | 2023-09-03 | 363 | 2024-08-31 | 0 | 0 | 10 | 10 | 20 | 30 | 50 | 80 | 120 | 140 | 170 | 200 | 250 | 320 | 400
FEEDBACK & QC | ZAK | 2023-09-03 | 363 | 2024-08-31
Q - Closing | ZAK | 2023-09-03 | 363 | 2024-08-31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Sitemap
[5 empty] | Font End | Creative | Performance | Post Launch
SN | Page Name | Page URL | Index? | Published | QC 01 | QC 02 | QC 03 | Final QC
1 | Home
2 | User Profile
3 | -- Sign up
4 | -- Login
5 | -- Forget Password
6 | Company
7 | -- Listing
8 | -- Company Detail
9 | Category
10 | -- Listing
11 | -- Category Detail
12 | Product
13 | -- Listing
14 | -- Product Detail
15 | City Page
16 | -- City Listing
17 | -- City Detail
18 | About Us
19 | -- Business Profile
20 | -- Meet the team
21 | -- Reviews
22 | -- Affiliations
23 | -- Contact Us
24 | -- Blog
25 | -- Terms of Use
-- ETC

## Sep 23
Domain: | konnectingdots.com |  |  | Action Items | Who | Deadline
Month: | 2023-08-01 |  |  | Blog or Article | ABIT
Account Manager: | Zakaria Mohammad |  |  | Verified Business Profile | ABIT
Date Range | 2023-08-01 | 2023-09-01 |  | Landing Page | ABIT
Updated By: | Zakaria Mohammad |  |  | City Page | ABIT
Content Reports | Current Month | Last Month | Variance | Content Strategy for Sep 2023 | Approved | Published
Blog | 0 | 0 | 0
Business Profile | 0 | 0 | 0
Landing Page | 0 | 0 | 0
City Page | 0 | 0 | 0
Static Page | 0 | 0 | 0
Review Added | 0 | 0 | 0
Facebook Post | 0 | 0 | 0
Linkedin Post | 0 | 0 | 0
GBP Post | 0 | 0 | 0
SEO Report
Google SEO Reports | New Count | Previous Count | Variance | SEO Strategy for Sep 2023 | Approved | Published
# of Pages - Published | 0 | 0 | 0
# of Pages - Indexed | 0 | 0 | 0
# of Business Profile - Published | 0 | 0 | 0
# of Business Profile - Indexed | 0 | 0 | 0
# of Landing Page - Published | 0 | 0 | 0
# of Landing Page - Indexed | 0 | 0 | 0
# of City Pages - Published | 0 | 0 | 0
# of City Pages - Indexed | 0 | 0 | 0
# of Static Page - Published | 0 | 0 | 0
# of Static Page - Indexed | 0 | 0 | 0
# of Review - Published | 0 | 0 | 0
# of Review - Indexed | 0 | 0 | 0
# of Google Listing | 0 | 0 | 0
Review Report | New Count | Previous Count | Comments | SMM Strategy for Sep 2023
Website Review Counts | 208 | 196 | 12 | Google Business Profile
Avg Rating: | 4.89 | 4.5 | 0.39 | Facebook Post
Approved for Site | 140 | 49 | 91 | Linkedin Post
Site Review Rating |  | 5 | -5 | Instagram
Not Approved for Site |  | 80 | -80 | Youtube Video
5 Stars |  |  | 0
4 Stars |  |  | 0
3 Stars |  |  | 0
2 Stars |  |  | 0
1 Stars |  |  | 0
3rd Party Reviews |  | 3 | -3 | 3rd Party Listing
Testimonial | 4 | 4 | 0
aHrefs Report | New Count | Previous Count | Comments | Competitor A | Competitor B | Competitor C | Competitor D | Competitor E | BPROPERTY | BTI | ASSURE | YEAR-BY-YEAR
aHrefs Rank | 0 | 0 | 0
URL Rating (UR) | 0 | 0 | 0
Domain Rating (DR) | 0 | 0 | 0
Backlinks | 0 | 0 | 0
Referring Domains | 0 | 0 | 0
Organic Keywords | 0 | 0 | 0
Organic Traffic | 0 | 0 | 0
Traffic Value | 0 | 0 | 0
GA Traffic Report | New Count | Previous Count | Updates | Target Keyword | Current Possition | Previous Position | Change
# of Users |  |  | 0 |  |  |  | 0
New Users |  |  | 0 |  |  |  | 0
Sessions |  |  | 0 |  |  |  | 0
Sessions Per User |  |  | 0 |  |  |  | 0
Pageviews |  |  | 0 |  |  |  | 0
Session Duration |  |  | 0:00 |  |  |  | 0
Bounce Rate |  |  | 0% |  |  |  | 0
Desktop Users |  |  | 0 |  |  |  | 0
Mobile |  |  | 0 |  |  |  | 0
Tablet |  |  | 0 |  |  |  | 0
Demographics - Male |  |  | 0% |  |  |  | 0
Demographics - Female |  |  | 0% |  |  |  | 0
GEO: Bangladesh |  |  | 0 |  |  |  | 0
GEO: US |  |  | 0 |  |  |  | 0
GEO: India |  |  | 0 |  |  |  | 0
Acquisition: Organic |  |  | 0 |  |  |  | 0
Acquisition: Direct |  |  | 0 |  |  |  | 0
Acquisition: Referral |  |  | 0 |  |  |  | 0
Acquisition: Social |  |  | 0 |  |  |  | 0
Social Media Report | New Count | Previous Count | Updates
FB Likes |  |  | 0
FB Follow |  |  | 0
Post Last Months |  |  | 0
FB Impression |  |  | 0
Google Rating |  |  | 0
Google Review Count |  |  | 0
Google Post Last Month |  |  | 0
Directory Listing |  |  | 0
Other Marketing Channels