## Overall
Overall Suggestion
SN | What | Who | When | Consult Note | Review 01 | Review 02 | Release Note | Action Point | Timeline | Priority | Responsible
1 | Keep sub domains clear and optimized. | [6 empty] | Sub domain disallowed |  | N/A
2 | Publicize your WHOIS information. | [6 empty] | Make it Public with the content of original business address | 16 aug'23 | P1 | Matiar Rahman
3 | Search console, malware, hack fixing | [6 empty] | Provide Access to ABIL, Check every week (Res: ABIL/BQ) | 14-aug'23 | P1 | Matiar Rahman
4 | SSL certificate with browsing experience | [6 empty] | SSL does not go down (Res: BQ) |  | N/A
5 | Responsibility Testing | [6 empty] | Initial Test report will be sent by ABIL (within Thursday 17 aug'23), KD Team, diff location, diff device, diff browser, diff OS - Testing & feedback will be given to ABIL | 21-Aug'23 | P2 | KD Team
6 | Optimize your robots.txt file. | [6 empty] | All pages, Image folder, multimedia will be publicly allowed & other info will be locked, sample robot.txt file will be shared by ABIL | sample: 16-Aug'23 BQ: 17-Aug'23 | P2 | ABIL & KD Team
7 | Keep your URLs static | [6 empty] | URL/Anchor optimization following best practices, 4 points to remember: 1. Lower case without special character, 2. Primary keyword focused, 3. Readable short url, 4. Eliminate unnecessary preposition/conjunction | 21-Aug'23 | P1 | Mostofa Zaman & KD Dev
8 | Organize your URLs logically with a breadcrumbs trail | [6 empty] | Home" should be replaced with icon/KD, Blogs > Blog, About > About us | 17-Aug'23 | P1 | Rayhan Safin
9 | Create and upload an XML sitemap | [6 empty] | TBD, dependent on 7 & 8 | TBD | P2
10 | Create an HTML sitemap | [6 empty] | Create HTML Sitemap (e.g apple.com/sitemap), dependent on 9 | TBD | P2 | Mostofa Zaman & Jubayer Rahman
11 | Ensure your content loads correctly | [6 empty] | ABIL will provide DOM structure | 28-Aug;23 | P2 | ABIL & KD Team
12 | Improve your navigation | [6 empty] | Inject Link ? will be discussed later. | TBD | N/A
13 | Maximize your page loading speed | [6 empty] | https://pagespeed.web.dev/ | TBD | P3 | KD Dev
14 | W3 Validated Codes | [6 empty] | https://validator.w3.org/ | TBD | P3
15 | Find and eliminate broken links | [6 empty] | https://www.deadlinkchecker.com/ |  | P3
16 | Fix 404 errors (for the most part) | [6 empty] | Need to be resolved with good user experience, (New Design need to be implemented) |  | P2 | Mostofa Zaman & Jubayer
17 | Social share options | [6 empty] | Social share plug-in in every page |  | P3
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100

## Draft
Overall Suggestion
SN | What | Who | When | Consult Note | Review 01 | Review 02 | Release Note
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100

## Checklist
SN | What | Who | When | Consult Note | Review 01 | Review 02 | Release Note | Status | Action Point | Timeline |  | Priority | Responsible
1 | Page Name (URL) | [6 empty] | N | Page Name convention should be created & followed |  |  | P1 | Mostofa Zaman & KD Dev
2 | Anchor Text | [6 empty] | Y | Need to be editable in admin panel |  |  | N/A
3 | Page Title (tag)* | [6 empty] | Y | Need to be editable in admin panel |  | Max 120 Characters | N/A
4 | Meta Description (tag), Tags | [6 empty] | Y | Need to be editable in admin panel |  | Max 220 Characters | Best practice will be followed | KD Dev
5 | Custom Head Tag | [6 empty] | N | Need to develop |  |  | TBD
6 | Custom Foot Tag | [6 empty] | N | Need to develop |  |  | TBD
7 | Publish / Unpublish Status | [6 empty] | Y |  |  |  | P1 | Rayhan safin
8 | Index Status | [6 empty] | Y | 4 options needed |  | Options will be given by ABIL | TBD
9 | Version Control: Original vs Current vs running | [6 empty] | N | Need to devlop |  | example will be given by ABIL | TBD
10 | Mode: HTML vs WYSIWYG | [6 empty] | Y |  |  |  | N/A
11 | Folder Structure | [6 empty] | N | Need to develop |  | Very Important (e.g image url, seo not possible) | P3 | Kd Dev
12 | 301 Redirection | [6 empty] | N | Need to develop |  |  | Best practice will be followed
13 | Keep your images formatted properly | [6 empty] | Y | Name, folder, dimension, alt tag |  |  | P1 | Jubayer & KD Dev
14 | Title your images appropriately, with proper alt tags | [6 empty] | Y | Name, folder, dimension, alt tag |  | Best Practice/convention will be shared by ABIL | P2 | KD Dev
15 | Feed with structured markup | [6 empty] | N | R & D, Need to develop |  |  | TBD
16 | Use internal links with descriptive anchor text | [6 empty] | Not needed
17 | Utilize rel=canonical tags | [6 empty] | N | R & D, Need to develop |  |  | TBD
18 | Include multimedia in your content | [6 empty] | N | Need to develop |  |  | TBD
19 | User generated content architecture for example: Encourage local reviews | [6 empty] | N | Need to develop |  |  | TBD
20 | Social share options | [6 empty] | discussed
21 | Offer social share icons in all your content | [6 empty] | discussed
22 | Make it easy for people to connect with you | [6 empty] | Y | chatbot, Whatsapp etc. |  |  | TBD
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100

## Onpage Testing
SN | What | Who | When | Consult Note | Review 01 | Review 02 | Release Note
1 | Page speed testing
2 | Schema Markup Testing Tool
3 | W3C Markup Validation Test
4 | Mobile-Friendly Test
5 | Broken Link Checker
6 | SEO OnPage Check
7 | OpenGraph Checker
8 | Content Analysis - SEO Review Tools
9 | SEO friendly HTML checking
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100